## TechSprint Workplan
TechSprint Workplan
DATE UPDATED |  |  | [Date]
PROJECT TITLE |  |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  |  | [Project Manager's name] |  |  |  |  | TECHSPRINT DATE | [6 empty] | [Final Date]
| TASK TITLE | COMMENTS | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | MONTH ONE | [19 empty] | MONTH TWO | [19 empty] | MONTH THREE | [19 empty] | MONTH FOUR | [19 empty] | MONTH FIVE | [19 empty] | MONTH SIX | [19 empty] | DEADLINE
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | TECHSPRINT
[8 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
1 | Introduction
1.1 | Project Plan |  |  |  |  | 0 | 0%
| Concept Development |  |  |  |  | 0 | 0%
| Concept Approval |  |  |  |  | 0 | 0%
| Update Project Plan / Set the TechSprint Date |  |  |  |  | 0 | 0%
1.2 | Spirit of theTechSprint |  |  |  |  | 0 | 0%
| Create/update spirit of the event |  |  |  |  | 0 | 0%
2 | TechSprint Planning
2.1 | Getting Started
Identify a Sprint Lead to oversee the project
Select workstream leads
| Assign workstreams and set up regular calls |  |  |  |  | 0 | 0%
| -External Communications Call |  |  |  |  | 0 | 0%
| -Data and Technology Call |  |  |  |  | 0 | 0%
| -Hacker Management Call |  |  |  |  | 0 | 0%
| -Logistics Call |  |  |  |  | 0 | 0%
| Sprint Lead to set up plan management details |  |  |  |  | 0 | 0%
| -Update workplan |  |  |  |  | 0 | 0%
| -Weekly planning call (internal) |  |  |  |  | 0 | 0%
| -Weekly planning call (partners) |  |  |  |  | 0 | 0%
| -Master contact list (host, venue, A/V, etc.) |  |  |  |  | 0 | 0%
2.2 | Problem Statement Definition and Development |  |  |  |  | 0 | 0%
| Build high-level visual process map (ongoing) |  |  |  |  | 0 | 0%
| Identify Expert Academics/Technologists |  |  |  |  | 0 | 0%
| Conduct Deep Dive Sessions w/industry experts (5-6) |  |  |  |  | 0 | 0%
| Define problem statement(s) |  |  |  |  | 0 | 0%
| Create list of refined problem statements (narrower in scope) |  |  |  |  | 0 | 0%
| Determine technology/data needs by problem statement |  |  |  |  | 0 | 0%
| Determine expertise needed by problem statement |  |  |  |  | 0 | 0%
| Socialize list with experts |  |  |  |  | 0 | 0%
| Socialize list with industry |  |  |  |  | 0 | 0%
| Rescope use cases |  |  |  |  | 0 | 0%
| Finalize use cases |  |  |  |  | 0 | 0%
| Assign/share/solicit use cases with hackers |  |  |  |  | 0 | 0%
2.3 | Partners
Identify appropriate partners (Agencies, Universities, advocates, etc.)
2.4 | TechSprint Design Considerations | Dummy dates, etc. |  |  |  | 0 | 0%
| Is there a winner? Will there be a prize? |  |  |  |  | 0 | 0%
| How will you structure company participation on hacking teams? |  |  |  |  | 0 | 0%
Who owns the intellectual capital?
Will you permit use of proprietary assets?
Will you permit use of data not provided by the TechSprint organizers?
Assign/share/solicit use cases with hackers
2.5 | Curate the TechSprint Teams
Select organizations to invite
Select individuals from those organizations to participate
Establish a process for inviting and screening participants
2.6 | Schedule of Events |  |  |  |  | 0 | 0%
| Confirm total days and main events |  |  |  |  | 0 | 0%
| Date/VIP constraints |  |  |  |  | 0 | 0%
| Confirm dates |  |  |  |  | 0 | 0%
| Draft schedule by day |  |  |  |  | 0 | 0%
| Agree on schedule internally |  |  |  |  | 0 | 0%
| Agree on schedule with host |  |  |  |  | 0 | 0%
| Agree on schedule with VIPs |  |  |  |  | 0 | 0%
| Hacker schedule (detailed) |  |  |  |  | 0 | 0%
| Observer Briefing schedule (detailed) |  |  |  |  | 0 | 0%
| Content Briefing schedule (detailed) |  |  |  |  | 0 | 0%
| Demo Day schedule (detailed) |  |  |  |  | 0 | 0%
| Send schedule to hackers |  |  |  |  | 0 | 0%
| Send schedule to observers |  |  |  |  | 0 | 0%
| Send schedule to Demo Day attendees |  |  |  |  | 0 | 0%
| Create detailed Run of Show (ROS) |  |  |  |  | 0 | 0%
| Run through ROS internally |  |  |  |  | 0 | 0%
| Run through ROS with host |  |  |  |  | 0 | 0%
| Run through ROS with venue |  |  |  |  | 0 | 0%
| Run through ROS with A/V team |  |  |  |  | 0 | 0%
| Run through ROS with relevant vendors (photo/video) |  |  |  |  | 0 | 0%
| Finalized ROS |  |  |  |  | 0 | 0%
| Print ROS for organizing team |  |  |  |  | 0 | 0%
2.7 | Budget
Set overall TechSprint budget
Create a budget plan to track expenses
2.8 | Possible Sponsorship Opportunities |  |  |  |  | 0 | 0%
| Decide sponsor v. in-house |  |  |  |  | 0 | 0%
| Define sponsorship parameters |  |  |  |  | 0 | 0%
| Define sponsorship levels |  |  |  |  | 0 | 0%
| Source monetary sponsors |  |  |  |  | 0 | 0%
| List sponsor in printed materials |  |  |  |  | 0 | 0%
| List sponsor in invitations |  |  |  |  | 0 | 0%
| List sponsor in presentations |  |  |  |  | 0 | 0%
| Sponsor speaking slot |  |  |  |  | 0 | 0%
| Other sponsor benefits |  |  |  |  | 0 | 0%
3 | Data, Platforms, and Internet Access
3.1 | Data |  |  |  |  | 0 | 0%
| Define ideal data sets |  |  |  |  | 0 | 0%
| Identify type of data needed (real or synthetic) |  |  |  |  | 0 | 0%
| Confirm whether outside data is allowed |  |  |  |  | 0 | 0%
| Reach out to potential data providers |  |  |  |  | 0 | 0%
| Compare prices of synthetic data |  |  |  |  | 0 | 0%
| Compare quality of synthetic data |  |  |  |  | 0 | 0%
| Understand provider constraints |  |  |  |  | 0 | 0%
| Contract with data provider |  |  |  |  | 0 | 0%
| Confirm dedicated onboarding resources |  |  |  |  | 0 | 0%
| Confirm dedicated onsite resources |  |  |  |  | 0 | 0%
| Data blueprint from provider |  |  |  |  | 0 | 0%
| Engage data protection/legal specialists |  |  |  |  | 0 | 0%
| Technologist to access data |  |  |  |  | 0 | 0%
| Technologist to test data |  |  |  |  | 0 | 0%
| Test data onsite |  |  |  |  | 0 | 0%
| Create summary of data ecosystem (data dictionary) |  |  |  |  | 0 | 0%
| Share summary of ecosystem with hackers |  |  |  |  | 0 | 0%
| Sample data provided to hackers |  |  |  |  | 0 | 0%
3.2 | Platforms |  |  |  |  | 0 | 0%
| Reach out to potential platform providers |  |  |  |  | 0 | 0%
| Compare prices/sponsorships of platforms |  |  |  |  | 0 | 0%
| Understand platform constraints |  |  |  |  | 0 | 0%
| Secure credit for computing power |  |  |  |  | 0 | 0%
| Computing needs analysis |  |  |  |  | 0 | 0%
| Feedback to platform providers |  |  |  |  | 0 | 0%
| Contract with platform provider |  |  |  |  | 0 | 0%
| Confirm dedicated onboarding resources |  |  |  |  | 0 | 0%
| Confirm dedicated onsite resources |  |  |  |  | 0 | 0%
| Test platforms onsite |  |  |  |  | 0 | 0%
3.3 | Onboarding and Troubleshooting |  |  |  |  | 0 | 0%
| Connect data and platform providers |  |  |  |  | 0 | 0%
| Testing Sessions: |  |  |  |  | 0 | 0%
| - Platform credentialing and setup |  |  |  |  | 0 | 0%
| - ETL (extract, transform, load) of data |  |  |  |  | 0 | 0%
| - Completeness and correctness of data set |  |  |  |  | 0 | 0%
| - Moving and processing data on the platform |  |  |  |  | 0 | 0%
| - Access to data in easily queried format |  |  |  |  | 0 | 0%
| - Onsite testing |  |  |  |  | 0 | 0%
| Collect platform preferences from hackers |  |  |  |  | 0 | 0%
| Platforms onboard hackers |  |  |  |  | 0 | 0%
| Share data and platform resources with hackers |  |  |  |  | 0 | 0%
| Give access to sample data to hackers |  |  |  |  | 0 | 0%
| Situate onsite resources |  |  |  |  | 0 | 0%
3.4 | Internet Access |  |  |  |  | 0 | 0%
| Test onsite wifi capacity |  |  |  |  | 0 | 0%
| Broadband cables |  |  |  |  | 0 | 0%
| Wifi hotspots |  |  |  |  | 0 | 0%
| Wifi boosters (optional) |  |  |  |  | 0 | 0%
| Test data onsite with wifi |  |  |  |  | 0 | 0%
| Test platforms onsite with wifi |  |  |  |  | 0 | 0%
| Test all room locations (blackout spots) |  |  |  |  | 0 | 0%
4 | Team Formation and Hacker Management
4.1 | Ground Rules |  |  |  |  | 0 | 0%
| Create/update ground rules |  |  |  |  | 0 | 0%
| Add rules to decks |  |  |  |  | 0 | 0%
| Add rules to collaboration tool |  |  |  |  | 0 | 0%
| Reiterate rules during Bootcamp |  |  |  |  | 0 | 0%
| Reiterate rules at TechSprint opening |  |  |  |  | 0 | 0%
| Reiterate rules in TechSprint follow-up |  |  |  |  | 0 | 0%
| Enforce rules |  |  |  |  | 0 | 0%
4.2 | Team Roles |  |  |  |  | 0 | 0%
| Modify/refine team roles |  |  |  |  | 0 | 0%
| Set rules for team formation |  |  |  |  | 0 | 0%
4.3 | Recruiting and Registration |  |  |  |  | 0 | 0%
| Assign hacker point of contact |  |  |  |  | 0 | 0%
| Create/update hacker invite list |  |  |  |  | 0 | 0%
| Draft expression of interest email |  |  |  |  | 0 | 0%
| Send expression of interest email |  |  |  |  | 0 | 0%
| Collect recommendations for hackers |  |  |  |  | 0 | 0%
| Draft pro forma invitations |  |  |  |  | 0 | 0%
| Create registration survey/link |  |  |  |  | 0 | 0%
| Create invitation pack |  |  |  |  | 0 | 0%
| Review invitation pack |  |  |  |  | 0 | 0%
| Finalize invitation pack |  |  |  |  | 0 | 0%
| Send pro forma invitation + packs |  |  |  |  | 0 | 0%
| Phone calls with interested companies/hackers |  |  |  |  | 0 | 0%
| Create/update hacker release form |  |  |  |  | 0 | 0%
| Send/collect hacker release forms |  |  |  |  | 0 | 0%
| Record confirmed hackers |  |  |  |  | 0 | 0%
| Record preferred platform (if needed) |  |  |  |  | 0 | 0%
| Record other items (dietary, disability, etc.) |  |  |  |  | 0 | 0%
| Follow up on hacker invitations (monthly) |  |  |  |  | 0 | 0%
| Confirmation email |  |  |  |  | 0 | 0%
| Assess skill set/team role gaps |  |  |  |  | 0 | 0%
| Tap backup/former hackers |  |  |  |  | 0 | 0%
4.4 | Team Formation/Collaboration
Identify team leads and scrum masters
Set number of teams
Set number of scrum masters
Host a Team leads call
Host a Scrum masters call (for multiple Scrum Masters)
Host Floaters call
Confirm roles
Reorganize teams (if necessary)
4.5 | Collaboration Tools |  |  |  |  | 0 | 0%
| Set up Slack channel |  |  |  |  | 0 | 0%
| Set up collaboration tool |  |  |  |  | 0 | 0%
| Upload hacker info (names, roles, pics, etc.) |  |  |  |  | 0 | 0%
| Invite hackers to Slack channel |  |  |  |  | 0 | 0%
| Invite hackers to collaboration tool |  |  |  |  | 0 | 0%
| Invite data/platform providers to Slack |  |  |  |  | 0 | 0%
| Invite data/platform providers to collaboration tool |  |  |  |  | 0 | 0%
4.6 | Hacker Boot Camp |  |  |  |  | 0 | 0%
| Schedule date/time/location (in-person) |  |  |  |  | 0 | 0%
| Send out Boot Camp invite to hackers |  |  |  |  | 0 | 0%
| Set up webex for remote attendees |  |  |  |  | 0 | 0%
| Reach out to Boot Camp speakers (content) |  |  |  |  | 0 | 0%
| Confirm data presenter |  |  |  |  | 0 | 0%
| Confirm platform presenter(s) |  |  |  |  | 0 | 0%
| Create/update Boot Camp Materials |  |  |  |  | 0 | 0%
| Create Boot Camp agenda |  |  |  |  | 0 | 0%
| Set up drinks post-Boot Camp |  |  |  |  | 0 | 0%
| Record Boot Camp |  |  |  |  | 0 | 0%
| Send recording and follow-ups |  |  |  |  | 0 | 0%
4.7 | During the TechSprint |  |  |  |  | 0 | 0%
| Set/communicate deadline for team formation |  |  |  |  | 0 | 0%
| Set/communicate deadline for problem statement selection |  |  |  |  | 0 | 0%
| Confirm team formation (deadline) |  |  |  |  | 0 | 0%
| Confirm problem statement selection (deadline) |  |  |  |  | 0 | 0%
| Book separate room for scrum sessions |  |  |  |  | 0 | 0%
| Schedule/communicate scrum sessions |  |  |  |  | 0 | 0%
| Set up midweek social (optional) |  |  |  |  | 0 | 0%
| Book rooms for demo practice (one per team) |  |  |  |  | 0 | 0%
| Brief doctors for demo practice |  |  |  |  | 0 | 0%
| Set/communicate deadline and format for demos |  |  |  |  | 0 | 0%
| Final deadline reminder to hackers |  |  |  |  | 0 | 0%
| Collect/collate demos |  |  |  |  | 0 | 0%
| Test demos onsite |  |  |  |  | 0 | 0%
5 | Logistics and Operations
5.1 | Event Overview |  |  |  |  | 0 | 0%
| Summary of Solution-Building |  |  |  |  | 0 | 0%
| Summary of Demo Day |  |  |  |  | 0 | 0%
| Summary of Observer Briefings (optional) |  |  |  |  | 0 | 0%
| Summary of Afterparty (optional) |  |  |  |  | 0 | 0%
5.2 | Venue |  |  |  |  | 0 | 0%
| Find appropriate space |  |  |  |  | 0 | 0%
| Contract with venue |  |  |  |  | 0 | 0%
| Meeting with all relevant venue staff |  |  |  |  | 0 | 0%
| Confirm/Discuss: |  |  |  |  | 0 | 0%
| - Bathroom access |  |  |  |  | 0 | 0%
| - Venue escorts |  |  |  |  | 0 | 0%
| - Onsite point of contact |  |  |  |  | 0 | 0%
| - Enough capacity/rooms |  |  |  |  | 0 | 0%
| - Building hours available |  |  |  |  | 0 | 0%
| - Building accessibility |  |  |  |  | 0 | 0%
| - A/C and heating (extended hours) |  |  |  |  | 0 | 0%
| - Event signage |  |  |  |  | 0 | 0%
| - Storage |  |  |  |  | 0 | 0%
| - Rain/snow contingency |  |  |  |  | 0 | 0%
| Book rooms: |  |  |  |  | 0 | 0%
| - TechSprint Floor |  |  |  |  | 0 | 0%
| - Demo Day Auditorium |  |  |  |  | 0 | 0%
| - Extra conference rooms |  |  |  |  | 0 | 0%
| - Observer briefings room |  |  |  |  | 0 | 0%
| - Demo Day hacker room (optional) |  |  |  |  | 0 | 0%
| - Power resources |  |  |  |  | 0 | 0%
| - White boards and teaming tools |  |  |  |  | 0 | 0%
| Confirm room setup |  |  |  |  | 0 | 0%
| Share list of attendees (security) |  |  |  |  | 0 | 0%
| Demo Day point person at venue |  |  |  |  | 0 | 0%
| Coordinate volunteers |  |  |  |  | 0 | 0%
| Front desk/check in setup |  |  |  |  | 0 | 0%
| Talk through event (verbal walk through) |  |  |  |  | 0 | 0%
| Room walk through |  |  |  |  | 0 | 0%
| Run of show walk through |  |  |  |  | 0 | 0%
| Room setup |  |  |  |  | 0 | 0%
5.3 | Food/Drink (consider multiple rooms) |  |  |  |  | 0 | 0%
| Order: |  |  |  |  | 0 | 0%
| - Breakfast |  |  |  |  | 0 | 0%
| - Coffee |  |  |  |  | 0 | 0%
| - Water |  |  |  |  | 0 | 0%
| - Other beverages |  |  |  |  | 0 | 0%
| - Snacks |  |  |  |  | 0 | 0%
| - Happy hour (optional) |  |  |  |  | 0 | 0%
| Options for dietary restrictions |  |  |  |  | 0 | 0%
5.4 | Audio/Visual |  |  |  |  | 0 | 0%
| Decide whether to outsource |  |  |  |  | 0 | 0%
| A/V requirements list |  |  |  |  | 0 | 0%
| A/V point of contact (venue) |  |  |  |  | 0 | 0%
| A/V point of contact (third party) |  |  |  |  | 0 | 0%
| Decide whether to livestream |  |  |  |  | 0 | 0%
| Select livestream platform |  |  |  |  | 0 | 0%
| Select messaging channel for real-time updates |  |  |  |  | 0 | 0%
| Contingency plan |  |  |  |  | 0 | 0%
| Testing sessions: |  |  |  |  | 0 | 0%
| - Connection (2x) |  |  |  |  | 0 | 0%
| - Audio and visual quality (2x) |  |  |  |  | 0 | 0%
| - Run of show (2x) |  |  |  |  | 0 | 0%
| - Contingency plan |  |  |  |  | 0 | 0%
| - Demo testing (day before) |  |  |  |  | 0 | 0%
| - Demo Day testing (early morning) |  |  |  |  | 0 | 0%
| - Audio/mics |  |  |  |  | 0 | 0%
| - Visuals/videos/presentations |  |  |  |  | 0 | 0%
| - Clicker |  |  |  |  | 0 | 0%
| Event laptop(s) |  |  |  |  | 0 | 0%
| Dedicated A/V staff |  |  |  |  | 0 | 0%
| Train host on A/V |  |  |  |  | 0 | 0%
| A/V set up |  |  |  |  | 0 | 0%
| Livestream set up |  |  |  |  | 0 | 0%
| Presentation set up |  |  |  |  | 0 | 0%
5.5 | Speakers
Identify potential keynote speakers
Identify potential partner/sponsor speakers
Identify other speakers
Send invitation email and pack to all potentials
Confirm speakers
Deadline for speakers' slides
Collate and test speakers' slides
Brief speakers on presentation setup
Speaker ribbon for name tags
Speaker dry-run
Mic speakers before stage (lavalier)
5.6 | Judging
Decide whether judging demos
Define judging criteria
Create judging scorecard
Decide if category for People's Choice
Set up People's Choice voting platform
Create Judging Deck
Identify potential judges
Send invitation email and pack to all potentials
Confirm judges
Confirm Chairperson of judging panel
Update Judging Deck with confirmed judges
Judge ribbon for name tags
Reserved seats for judges in front row
Judging pack (scorecards, rules, judge bios)
Designated judge liaison
Reserve conference room for deliberation
Judges announce winners
| Order and inscribe awards |  |  |  |  | 0 | 0%
| Confirm timer/buzzer for demos |  |  |  |  | 0 | 0%
| Source volunteers |  |  |  |  | 0 | 0%
| Assign volunteer manager |  |  |  |  | 0 | 0%
| Assign time slots to volunteers |  |  |  |  | 0 | 0%
| Create communication channel |  |  |  |  | 0 | 0%
| Instructions to volunteers |  |  |  |  | 0 | 0%
5.7 | Risk Mitigation
Sourcing hackers/attendees
TechSprint attendance level
Data procurement
Data access for hackers
Platform access for hackers
Wifi capacity at the TechSprint site
Team Dysfunction and breakdown
Onsite logistics
Demo Day Attendance
Award impact on collaboration
Demo Day technology failures
6 | Communications
6.1 | Messaging |  |  |  |  | 0 | 0%
| Develop narrative and the strategic messages |  |  |  |  | 0 | 0%
| One-pager on the TechSprint |  |  |  |  | 0 | 0%
6.2 | Graphics |  |  |  |  | 0 | 0%
| Source graphic designer (in-house or freelance) |  |  |  |  | 0 | 0%
| Brainstorm image and branding |  |  |  |  | 0 | 0%
| Contract with graphic designer |  |  |  |  | 0 | 0%
| Consistent branding |  |  |  |  | 0 | 0%
| Main image |  |  |  |  | 0 | 0%
| Sticker image |  |  |  |  | 0 | 0%
| Full poster image |  |  |  |  | 0 | 0%
| Other fonts |  |  |  |  | 0 | 0%
| Other images |  |  |  |  | 0 | 0%
| Template PPT/Google Slides |  |  |  |  | 0 | 0%
| Basic visual - poster of the event |  |  |  |  | 0 | 0%
6.3 | Event Website and App |  |  |  |  | 0 | 0%
| Website creation |  |  |  |  | 0 | 0%
| - TechSprint overview |  |  |  |  | 0 | 0%
| - Logistics (date and location) |  |  |  |  | 0 | 0%
| - Registration form (hackers and attendees) |  |  |  |  | 0 | 0%
| - Information on sponsors and organizers |  |  |  |  | 0 | 0%
| - Data resources/repository (optional) |  |  |  |  | 0 | 0%
| Mobile App Creation |  |  |  |  | 0 | 0%
| - Detailed schedule |  |  |  |  | 0 | 0%
| - Speaker profiles |  |  |  |  | 0 | 0%
| - Attendee bios (self-created) |  |  |  |  | 0 | 0%
| - Attendee messaging |  |  |  |  | 0 | 0%
| - Feedback on specific sessions |  |  |  |  | 0 | 0%
| - Automated mass communication tool (optional) |  |  |  |  | 0 | 0%
6.4 | Social Media and Press Planning |  |  |  |  | 0 | 0%
| Align with hosts/partners on branding |  |  |  |  | 0 | 0%
| Draft communications guidelines |  |  |  |  | 0 | 0%
| Advance press release |  |  |  |  | 0 | 0%
| Include guidelines in invitation packs and website |  |  |  |  | 0 | 0%
| Select press outlets to invite |  |  |  |  | 0 | 0%
| Draft press invitation letter |  |  |  |  | 0 | 0%
| Send press invitation letters and packs |  |  |  |  | 0 | 0%
| Press phone briefing |  |  |  |  | 0 | 0%
| Press ribbon for name tags |  |  |  |  | 0 | 0%
| Conference room for press interviews |  |  |  |  | 0 | 0%
| Create event hashtag |  |  |  |  | 0 | 0%
| Model correct hashtag/formatting |  |  |  |  | 0 | 0%
| Social media posting plan |  |  |  |  | 0 | 0%
| - Bootcamp (4-6 weeks out) |  |  |  |  | 0 | 0%
| - Announcement of teams (2 weeks out) |  |  |  |  | 0 | 0%
| - TechSprint opening (each presentation) |  |  |  |  | 0 | 0%
| - TechSprint Day 1 Highlights |  |  |  |  | 0 | 0%
| - TechSprint Day 2 Highlights |  |  |  |  | 0 | 0%
| - TechSprint Day 3 Highlights |  |  |  |  | 0 | 0%
| - Demo Day opening (each presentation/keynote) |  |  |  |  | 0 | 0%
| - Team demos (1-2 teams) |  |  |  |  | 0 | 0%
| - Award presentation |  |  |  |  | 0 | 0%
6.5 | Post-Sprint Press Planning |  |  |  |  | 0 | 0%
| Draft event summary |  |  |  |  | 0 | 0%
| Draft press release |  |  |  |  | 0 | 0%
| Draft op-ed |  |  |  |  | 0 | 0%
| Draft follow up emails (by segment) |  |  |  |  | 0 | 0%
| Draft feedback survey (by segment) |  |  |  |  | 0 | 0%
6.6 | Photos/Videos |  |  |  |  | 0 | 0%
| Centralized photo/video repository |  |  |  |  | 0 | 0%
| Reach out to photographer |  |  |  |  | 0 | 0%
| Reach out to videographer |  |  |  |  | 0 | 0%
| Contract with photographer |  |  |  |  | 0 | 0%
| Contract with videographer |  |  |  |  | 0 | 0%
| Book room for interviews |  |  |  |  | 0 | 0%
| ROS for photographer |  |  |  |  | 0 | 0%
| ROS for videographer |  |  |  |  | 0 | 0%
| Shot list - photographer |  |  |  |  | 0 | 0%
| Shot list - videographer |  |  |  |  | 0 | 0%
| Interview list + questions |  |  |  |  | 0 | 0%
| Photographer setup |  |  |  |  | 0 | 0%
| Videographer setup |  |  |  |  | 0 | 0%
| Photographer test |  |  |  |  | 0 | 0%
| Videographer test |  |  |  |  | 0 | 0%
6.7 | Decks and Presentations
Hacker Information Deck (hackers)
Invitation Deck (observers and attendees)
Judging Deck (judges and hackers)
Boot Camp presentation for hackers
TechSprint Opening + Keynote (collated)
Observer Briefings
Demo Day Opening + Keynotes (collated)
Demo Day Demos (collated)
Embed videos
6.8 | Printed Materials |  |  |  |  | 0 | 0%
| Identify local printer |  |  |  |  | 0 | 0%
| Meet with printing manager |  |  |  |  | 0 | 0%
| Print signs |  |  |  |  | 0 | 0%
| Step and Repeat |  |  |  |  | 0 | 0%
| T-shirts |  |  |  |  | 0 | 0%
| Print takeaways/programs |  |  |  |  | 0 | 0%
| Print press kit |  |  |  |  | 0 | 0%
| Print judges background pages |  |  |  |  | 0 | 0%
| Print judging criteria and instructions |  |  |  |  | 0 | 0%
| Print judging scorecards |  |  |  |  | 0 | 0%
| Format name tags |  |  |  |  | 0 | 0%
| Print name tags (by event) |  |  |  |  | 0 | 0%
| Lanyard/clip/stuff name tags |  |  |  |  | 0 | 0%
| Blank name tags and markers |  |  |  |  | 0 | 0%
| Print stickers |  |  |  |  | 0 | 0%
| Print TechSprint Ground Rules |  |  |  |  | 0 | 0%
| Print important contacts |  |  |  |  | 0 | 0%
| Print table tents (wifi, password, etc.) |  |  |  |  | 0 | 0%
7 | TechSprint Follow-up
7.1 | Post-Sprint Action Items |  |  |  |  | 0 | 0%
| Collect names of attendees and no-shows (volunteer) |  |  |  |  | 0 | 0%
| Publish press release |  |  |  |  | 0 | 0%
| Publish op-ed |  |  |  |  | 0 | 0%
| Update website |  |  |  |  | 0 | 0%
| Social media post(s) |  |  |  |  | 0 | 0%
| Post-event press follow up/monitoring |  |  |  |  | 0 | 0%
| Send pre-drafted emails (by segment) |  |  |  |  | 0 | 0%
| Send thank you notes to speakers |  |  |  |  | 0 | 0%
| Send thank you notes to judges |  |  |  |  | 0 | 0%
| Thank you to volunteers |  |  |  |  | 0 | 0%
| Prize follow-ups with host/sponsor |  |  |  |  | 0 | 0%
| Prize follow-ups with winning team(s) |  |  |  |  | 0 | 0%
| Internal debrief |  |  |  |  | 0 | 0%
| Debrief with host organization |  |  |  |  | 0 | 0%
| Debrief with venue + other vendors |  |  |  |  | 0 | 0%
| Collect survey responses |  |  |  |  | 0 | 0%
| Schedule focus groups (by segment) |  |  |  |  | 0 | 0%
| Host focus groups (by segment) |  |  |  |  | 0 | 0%
| Update TechSprint Manual |  |  |  |  | 0 | 0%
| Track press |  |  |  |  | 0 | 0%
| Compile demos in repository |  |  |  |  | 0 | 0%
| Compile data in repository |  |  |  |  | 0 | 0%